## Scope
FY27 IP Co-Sell — Scope
Source: Partner Sharing Redmond/India Sync (2026-06-16) + Teams chat (Soham's scope table, verbatim) + FY27 IP Co-Sell Requirements BRD.
# | Enhancement | Scope Item
1 | Data Model & Pipeline | Implement MBS vs DRACR credit path routing — Marketplace deals → MBS credit; Non-Marketplace → DRACR credit, classified at deal grain
2 | Data Model & Pipeline | Build SAP exception path — rename PRACR to "SAP Tenant Consumption," flag offline reporting, handle dual-credit dedup logic
3 | Data Model & Pipeline | Integrate FY27 IP Co-Sell target data from Finance (Ben Frisbee / Nathan Taylor) into dashboard measures
4 | Data Model & Pipeline | Add new rejection reason codes to ReasonsCalculatedTable: "Partner not in Top 25," "ACV below $25K," "PRACR ineligible (non-SAP)"
5 | Data Model & Pipeline | Implement duplicate detection in FactIPCoSell — prevent a deal from receiving both DRACR + MBS + SAP Tenant Consumption credit simultaneously
6 | Data Model & Pipeline | Update FY27 program changes
7 | Data Model & Pipeline | Remap Service Comp Groups (SCG) to FY27 taxonomy and load FY27 dollar exchange rates
8 | Reporting | Rename "Transition Partner Performance" tab to "IPCS Partner Performance"
9 | Reporting | Separate SAP from the 25 IP Co-Sell partners into a dedicated SAP tab
10 | Reporting | Retain PRACR metrics and deal registration visuals on SAP tab
11 | Reporting | Mirror IPCS Partner Performance structure with SAP-specific filters
12 | Reporting | Remove PRACR-related metrics and visuals from the 25-partner (IPCS) tab — retain deal registration and target metrics only
13 | Reporting | Remove "Deal Registration by Incentive Type" visual
14 | Reporting | Retain "Deal Registration by Segment" and "Deal Direction" visuals on IPCS tab
15 | Reporting | Remove Biz Apps Performance and Pipeline tabs
16 | Reporting | Integrate FY27 IP Co-Sell target data from Finance (Ben Frisbee / Nathan Taylor) into dashboard measures
Assumptions / Callouts
1 | DRACR core logic and 26-partner implementation already in place; expecting no changes post May
2 | PRACR is retired for all partners except SAP; SAP continues under renamed "SAP Tenant Consumption"
3 | SAP Dual Credit continuation is pending formal metric and compliance sign-off; if confirmed, we might need additional efforts depending on the scope change.
4 | Partner list is locked for FY27 — no mid-year additions
5 | ACV data source (Partner Revenue) would remain same as what we have from ReferralMasterPII.
6 | DCF S10 scoping is purely operational and does not need any change in logic
7 | FY27 target data source and grain must be confirmed with stakeholders before dashboard integration
8 | Biz Apps tab removal to be communicated to Biz Apps team by Savvy; escalations directed to Antoine Boris
9 | DRACR should be credited only if IP partner matches one of the exception partners.
10 | We will need SCG mapping from FD&E team (Padmaja's team)

## Items
FY27 IP Co-Sell — Action Items
Source: Partner Sharing Redmond/India Sync (2026-06-16) + Teams chat (Soham's scope table, verbatim) + FY27 IP Co-Sell Requirements BRD.
# | Action Item | Owner | Source
1 | Create/maintain ADO user story(ies) covering all the changes (under FY26 Q3/Q4 DRACR Planning). | Soham | Call / WorkIQ
2 | Add the reporting-change list (pinged list) to the BRD. | Soham | Call
3 | Obtain SCG mapping from FD&E (Padmaja's team). | Soham / Team | Chat
4 | Communicate Biz Apps tab removal to Biz Apps team; escalations -> Antoine Boris. | Savvy | Chat
5 | Test/implement the DRACR "CRA" calculation logic (~1-2 days; bifurcate on TPI deliverable), then demo to Soham. | Harshit | Call
6 | Set capacity/timeline: June 16-30 = 2 IP Co-Sell changes + 1 DRACR sustain (Soham offered 2+2); ~40 SP (~20 backend + ~20 reporting); target ~mid-July prod; provide Dev-complete / UAT / start-end milestones. | Soham + India team | Call
7 | Confirm FY27 target data source + grain with Finance before dashboard integration. | Soham -> Finance (Ben/Nathan) | Chat
8 | Check with Savvy on SPS segment + the impacted co-marketing report confirmation. | Soham | Call
9 | Walk through Soham's pinged requirements and build a timeline. | India team | Call

## Open Questions
FY27 IP Co-Sell — Open Questions
Source: Partner Sharing Redmond/India Sync (2026-06-16) + Teams chat (Soham's scope table, verbatim) + FY27 IP Co-Sell Requirements BRD.
# | Open Question | Status / Resolver | Source
1 | What does "Baseline Analysis" mean? Team finished BRD analysis and flagged this one section (has an image in BRD). | UNRESOLVED - BRD has no formal definition, only role refs (Finance "validates baselines"; Savvy/BI "supports baseline analysis"). Soham to ask author ("Reddy"). | Call / Chat / BRD
2 | Sign-off from Sai on the DRACR logic change. | NOT received (Arham raised it; Soham: no sign-off yet). | Call
3 | SAP Dual Credit (SAP RISE Dual Credit continuation). | PENDING formal metric + Compliance sign-off; extra effort if confirmed. | Chat / BRD
4 | FY27 target data - source & granularity. | Must be confirmed with stakeholders before integration. | Chat
5 | Who owns dual-credit handling (DataOps / Aman / Koshik / GPS)? | Unclear - "check with Aman once DataOps does that work". | Call
6 | S10 partner-count inconsistency (8 vs 10) and reseller eligibility. | Raised in BRD comments - unresolved. | BRD
7 | MBS feed granularity (rate not at Partner/Deal-ID level; columns only in upstream MHR, not in EDLP). | MBS team to propose an enhancement; ticket currently closed. | Call